## Product Backlog
User Story no | As A | I Want To | So that | Assigned Person
1001 | Admin | securely log in using my credentials | I can access the admin dashboard and manage user accounts. | Santhosh
1002 | Admin | view a list of all registered users | I can monitor user registrations and their status. | Mathavan Raj
1003 | Admin | review and verify documents uploaded by users | I can approve or reject their EMI card application. | Ramadoss
1004 | Admin | activate the user’s EMI card after verification | the user can start purchasing products using the card. | Seneha
1005 | Admin | suspend or deactivate user accounts when necessary | I can maintain security and compliance | Kamalesh
1006 | Admin | update product details | information stays accurate.
1007 | Admin | delete products | no longer available.
1008 | Admin | view all user transactions | I can track purchases.
1009 | Admin | view EMI schedules for each user | I can monitor payments.
1010 | Admin | activate a user’s EMI card after successful verification | the user can start purchasing products using the card.
1011 | Admin | add a product | users can purchase them on EMI

## Sprint Backlog and WBS
User Story no | Task List | Story Point | Assigned to | Status | Estimated Hours
1001 | Design Login UI | 1 | Santhosh | Completed | 2
| Implement Login API | 3 |  | Completed | 1
| Password Hashing | 2 |  | Completed | 1
| Session Management | 1 |  | Completed | 2
| Role Verification | 1 |  | Completed | 1
| Error Handling | 2 |  | Completed | 2
1002 | View the registered user by Admin | 3 | Mathavan Raj
| Create UI layout | 1 |  | Completed | 2
| Implement API Integration | 2 |  | Completed | 3
| Add Search functionality | 1 |  | Completed | 1
| Add filters functionality | 2 |  | Completed | 2
| Build Pagination Control | 3 |  | Completed | 2
| User details page | 1 |  | Completed | 2
| Display user account status | 2 |  | Completed | 2
1003 | Design UI screen for user verification list Frontend Dev | 2 | Ramadoss | Completed
| Create user detail & doc preview page Frontend Dev | 3 |  | Completed
| Open user details page Admin can click user and see full details To Do | 2 |  | Completed
| Show uploaded documents Documents should be visible clearly | 2 |  | Completed
| Add Approve/Reject buttons Admin can approve or reject user | 2 |  | Completed
| Request re-upload option Admin can ask user to upload again if unclear | 3 |  | Completed
| Update status in database System should store Approved/Rejected | 2 |  | Completed
| Send notification to user User should get message after approval/reject | 2 |  | Completed
1004 | Activate EMI Cards | 3 | Seneha
| Design EMI cards activation screen | 1 |  | completed | 2
| API to validate card details | 2 |  | completed | 3
| Generate OTP API | 1 |  | completed | 2
| Integarte OTP screen in UI | 2 |  | completed | 3
| Update card status to active | 1 |  | completed | 2
| Database table update for card status | 2 |  | completed | 3
| Front end-backend integration | 2 |  | completed | 2
1005 | Manage User Accounts | 3 | Kamalesh
| update user account status |  |  | completed
| Transaction monitoring | 2 |  | completed
| Budget and invoice | 3 |  | completed
| Payment and Receipt management | 2 |  | completed
| Reports and Dashboards | 3 |  | completed

## User Story
UserStory No | As a | I want | So that | Acceptance Criteria | Status
1001 | Admin | securely log in using my credentials, | I can access the admin dashboard and manage user accounts. | 1.Admin must enter a valid Admin ID/Username and Password. 2.System should validate credentials against the database. 3.Access should be granted only if credentials are correct. 4.Display clear error message for invalid credentials. 5.Passwords must be stored in hashed format (not plain text). 6.Implement session management (JWT or secure cookies). 7.Ensure role-based access control (only admins can access dashboard). | completed
1002 | Admin | view a list of all registered users | I can monitor user registrations and their status. | 1.The admin dashboard should display a list of all registered users with their details including Name, Email, Card Type, and Status 2.The system should allow the admin to filter users based on their status such as Pending, Approved, or Rejected. 3.The dashboard should support pagination so that large lists of users can be viewed easily. 4.The admin should be able to search for users by name or email to quickly locate specific profiles. 5.The dashboard should display the total number of users and also show counts for each status category. 6.If no users match the applied filter or search criteria, an empty state message should be displayed | completed
1003 | Admin | to view the submitted user documents | I can verify documents easily and approve/reject them based on correct | 1. Admin should be able to open a document view page 2. System must display uploaded documents clearly 3. Admin should see user details linked with document 4. Admin can download the document. 5. System must load documents without delay. 6. Error message should be shown if file is corrupted/not found | completed
1004 | Admin | activate a user’s EMI card after successful verification | the user can start purchasing products using the card. | 1.Admin must validate card details
2.Card details should be generated and linked to the user account.
3.Admin can change user status to “Active”.
4.System should notify the user via email/SMS about activation.
1005 | Admin | suspend or deactivate user accounts when necessary | I can maintain security and compliance. | 1.The admin should be able to deactivate or suspend user accounts directly from the dashboard. 2.Once an account is deactivated, the system must immediately restrict access for that user, preventing login or any actions. 3.The dashboard should clearly display the status of each user account, showing whether it is active, suspended, or deactivated. 4.All admin actions related to account suspension or deactivation must be logged for audit purposes, including timestamp, admin ID, and affected user ID. | completed